## Sheet1
NO | AKTIVITAS PROGRESS | Tanggal Mulai | Tanggal Berakhir | Durasi | PIC | STATUS |  | PLANNING TOOLS
1 | Menentukan Topik, Latar Belakang dan Contoh User Persona | 2025-05-07 | 2025-05-11 | 4 | Adrian, Alif, Desna | Selesai
2 | Membuat Prototype Wireframe dan Artikel Medium Masing Masing | 2025-05-07 | 2025-05-11 | 4 | Adrian, Alif, Desna | Selesai | Tools Name | Purpose | Usage
3 | Menyusun Pertanyaan Interview | 2025-05-07 | 2025-05-11 | 4 | Adrian | Selesai | Figma | UI/UX Design | Desain wireframe, prototyping
4 | Melakukan Wawancara/Interview | 2025-05-07 | 2025-05-11 | 4 | Adrian, Alif, Desna | Selesai | GitHub | Version Control & Collaboration | Pengumpulan artefak akhir (file figma, pdf, semua progress)
5 | Laporan Riset Wawancara Pengguna | 2025-05-07 | 2025-05-11 | 4 | Adrian | Selesai | Canva | Graphic Design | Desain user persona, empathy map
6 | Membuat User Persona | 2025-05-07 | 2025-05-11 | 4 | Desna | Selesai | Google Docs | Document editing & Collaboration | Penulisan laporan hasil riset pengguna
7 | Membuat Empathy Map | 2025-05-07 | 2025-05-11 | 4 | Desna | Selesai | Excell | Data Management & Analysis | Pengolahan data, Project Management
8 | Membuat User Journey & Scenario Mapping | 2025-05-07 | 2025-05-11 | 4 | Desna | Selesai | MS Word | Word Processing | Penulisan draf jurnal, uability goal, heuristic eval
9 | Requirement Analysis | 2025-05-07 | 2025-05-11 | 4 | Adrian | Selesai
10 | Membuat Wireframe & Low Fidelity Prototype | 2025-05-07 | 2025-05-11 | 4 | Adrian | Selesai
11 | Usability Goal & Heuristic Evalution | 2025-05-07 | 2025-05-11 | 4 | Adrian | Selesai
12 | Project Management & Planning Tools | 2025-05-07 | 2025-05-11 | 4 | Adrian, Alif, Desna | Selesai
13 | Draf Jurnal Ilmiah | 2025-05-07 | 2025-05-11 | 4 | Adrian | Selesai